## Slide 1: Risk Reduction at Ash Disposal Area No. 2 A Case Study TVA Johnsonville Fossil Plant New Johnsonville, Humphreys County, Tennessee
Presented By
Roberto L. Sanchez, PE and Stephen H. Bickel, PE

## Slide 2
Soon after the December 2008 dredge cell failure at its Kingston, TN fossil-power generating facility, TVA created an internal project management organization named Fossil Generation Development & Construction (FGD&C) to address potential geotechnical instability issues at all of its other plants’ Coal Combustion Products (CCP) storage facilities.
In the beginning ….

## Slide 3
TVA’s Eleven Fossil Plants
Mississippi
Alabama
Virginia
Georgia
Tennessee
North Carolina
Allen
3 Units 990 MW
Colbert
5 Units 1350 MW
Widows Creek
8 Units 1969 MW
Cumberland
2 Units 2600 MW;
Bull Run
1 Unit 950 MW
John Sevier
4 Units 800 MW
Kingston
9 Units 1700 MW
Johnsonville
10 Units 1485 MW
Gallatin
4 Units 1255 MW
Paradise
3 Units 2558 MW
Shawnee
10 Units 1750 MW
U10 idled

## Slide 4
Dry
Storage
Close all Wet Storage Facilities
Convert Wet CCP Processes to Dry Operation
(Fly Ash, Bottom Ash, and Gypsum)
Develop a Water Management Strategy for Plant Process Water
Implement Long Term Stability Improvements and Remediation to Existing CCP Facilities
FGD&C’s Programmatic Mission

## Slide 5
  Phase 1 – Facility Review
    Records Review/Staff Interviews
    Site Condition Review
    Recommendations for Future Analysis, Studies, and Program Improvements
    Final Report Issued June 24, 2009
  Phase 2 – Engineering Assessments
    Geotechnical Explorations
    Hydrologic and Hydraulic Analysis
    Dam Safety Hazard Classifications
    Spillway Inventories
FGD&C’s Highlights
  Program Goals
    Assess Structural Conditions of Impoundments
    Implement Improvements
  Program Statistics
    FY10 Man-hours ~ 472,324
    FY 09 Engineering Man-hours ~ 168,074
    Borings ~781 (47,000 ft of footage drilled)
    Instruments ~ 594
    Rock Placed ~ 455,305 tons
    Sand ~ 26,277 tons
  Phases 1,2,3 and 4 in Parallel

## Slide 6
  Phase 3 – Remediation Design and Construction
    Structural Deficiencies
    Improve Freeboard (Storage)
    Risk Reduction
  Phase 4 – Programmatic Improvements
    Dam Safety Inspection Training
    Programmatic Documents
CCP Projects & Engineering’s Highlights
Construction of Improvements at Bull Run

## Slide 7: Looking Forward – FGD&C’s Next Steps
Closure of all CCP Impoundments
Transition to Dry Storage.
Build Landfills
Construct Dewatering Facilities.
Implement Waste-Water and Storm-Water Management Strategies.
Evaluate Seismic Risks.

## Slide 8: Results of the Phase 1 Assessments
The Phase 1 Assessment performed for Ash Disposal Area No. 2 at TVA’s Johnsonville plant resulted in a high priority ranking with regards to needed risk reduction actions. The assessment uncovered the following issues of concern:
  A lack of adequate hydraulic freeboard;
  Seepage areas which had reportedly increased in size;
  Tall spillway risers that were leaning;
  Submerged spillway outlet pipes that regularly surged and had a history of sinkhole formations; and
  Steep exterior dike slopes with potentially low factors of safety.

## Slide 9: Presentation Outline
This presentation describes the Risk Reduction Program performed for JOF’s Ash Disposal Area No. 2. This facility was placed on a high priority list due to its environmentally sensitive location.
The presentation is divided in the following sections:
  Plant location and history;
  Ash Disposal No. 2 construction sequence;
  Results of Phase I Assessment;
  Risk Reduction Program; and
  Summary and Conclusions.

## Slide 10
Johnsonville Fossil Plant General Vicinity Map
Notes: Location is in west-central Tennessee - about 65 miles west of Nashville – one third the distance between Nashville and Memphis

## Slide 11
Kentucky Lake
Ash Disposal Area 2
Powerhouse
Johnsonville Fossil Plant Aerial View
Notes: Areal view showing the plant and Ash Disposal Area 2 surrounded by water.

## Slide 12
Johnsonville Fossil Plant Postcard Circa 1955
Notes: Just an interesting old post card found on e-bay. JOF is the second steam-electric project by TVA, currently the oldest in system. At completion it was one of the ten largest plants in the world.

## Slide 13
Johnsonville Fossil Plant Site Layout for Ash Disposal Area No. 2
previous flow direction
present flow direction
Notes: Island is 125 acres/87 within the dikes. Note ash stacking and storage on North end (mostly dry) separated by sluice channels in the middle, and the ash pond complex on the south end. Three sets of old spillways. Describe water flow.

## Slide 14: Johnsonville Fossil Plant Timeline for Ash Disposal Area No. 2
1949-1952 JOF Steam Plant Built. Boat Harbor (NE) & Condenser Channel (SE) Dikes built using hydraulic fill.
Mid 1960’s – Ash Disposal Area 1 reaching capacity & planning for Area 2 takes place.
1977 to 1978 – Ash Disposal Area 2 raised to Elev. 390, East spillway and Metal Waste Pond added.
1969 to 1970– Ash Disposal Area 2 built to Elev. 378. Hydraulic fill used in lower portions of West dike. North & South Spillways only.
During 1950’s to late 1960’s all ash sluiced north to Ash Disposal Area 1
1994 – Sink hole forms over one South Spillway, pipes slip lined, and middle spillway removed from service.
1994 to 1996 – Serious erosion at toe of West Dikes. Repairs w/ rip rap.
2009 Phase 1 Report, Phase 2 Geotech Study, New Spillways Designed & Installed
2002 – Slough on NE Dike forms, repairs w/ rip rap. Inspection reports that Seep 3A had increased in size.
1976 – Seepage Reported on NE Dike. Area repaired by excavating and replacing with clay. Seepage reappears later as ash pond raised.
Notes: Just run through timeline.

## Slide 15
Johnsonville Fossil Plant Construction Dredging the Condenser Intake Channel
Notes: Dikes constructed in 3 stages. First during 1948-1950. Dredge used to place hydraulic fill in boat harbor (Northeast) and condenser water channel (Southeast) dikes during original construction. Second stage in 1968 – 1970, third in 1978.

## Slide 16
  Phase I Facility Assessment Recommendations
    Monitor Seep 3A
    replace spillways,
    increase freeboard, and
    perform geotechnical study
  Geotechnical Study
    Began March, 2009, Final Report March, 2010
    Forty-eight borings drilled, sixty-eight existing boring logs reviewed
    Fourteen Cross-Sections investigated, eight analyzed
    Seepage & slope stability analyses using SEEP/W & SLOPE/W
    Recommended slope stability improvements to NE & SE Dikes
Johnsonville Ash Disposal Area 2 Phase 1 & Geotechnical Studies

## Slide 17
Minimum Freeboard Sluice Channel at Northwest Dike
Approximately one foot freeboard

## Slide 18
Steep/Irregular Slopes and Trees on Northeast Dike
Notes: Original view of NE Dike during Phase 1.

## Slide 19
Spillway Risers in Ash Stilling Pond
Notes: Existing spillway risers, 35 feet tall, slight tilt. Note middle riser has been inactive since 1990’s because it could not be slip-lined after the sinkhole formed on the dike slope.

## Slide 20
Air Surging from Spillway Outlet Pipes
Air surging from outlet pipes
Notes: Air surges from outlet ends of spillways, indicating pressure fluctuations within the pipes.

## Slide 21
Seepage Area 3A Collection Piping System for Monitoring
Notes: Established dry weather base flow 3500 gpd.

## Slide 22
Johnsonville Facility Geotechnical Exploration

## Slide 23
Johnsonville Facility Geotechnical Exploration

## Slide 24
Johnsonville Facility Generalized Dike Cross Section

## Slide 25
Historical Seepage Locations

## Slide 26
Typical Graph for Selection of Effective Stress Shear Strength Parameters

## Slide 27
Typical SLOPE/W Output File

## Slide 28
“As-Found” Slope Stability Factors of Safety

## Slide 29
  Spillways Replacement Project (New Spillways)
  North East Dike Slope Stability Improvement Project
  Spillways Abandonment Project (Close Old Spillways)
  South East Dike Slope Stability Improvement Project
  Other Risk Reduction Projects
    Relocate Sluice Channel from Northeast Dike
    Removed 860,000 tons Ash during 2010 or approximately 1/6 of the total ash impounded at the site.
    Extended Coal Yard Drainage Basin discharge pipe by 650 feet
    Improvements to Causeway & Roadway to Island
Johnsonville Ash Disposal Area 2 Risk Reduction Projects

## Slide 30
Siphon “Torpedo-Strainer” Inlet with Float Balls Attached

## Slide 31
Siphons in Operation During Pool Drawdown

## Slide 32
Aerial View During Spillway Replacement Project

## Slide 33
New Spillway Inlet Structures

## Slide 34
Outlet Headwall for New Spillways

## Slide 35
Spillway Horizontal Pipe
Spillway Riser Pipe
Grout Mixer and Pump Truck
Spillway Grouting Trench
Ash Stilling Pond
Dike
Spillways Improvements And Closures

## Slide 36
Grouting East Spillway Pipes Spillway Closure Project

## Slide 37
Helicopter Removing Skimmers from South Spillway Risers

## Slide 38
Steel Bulkheads for Grout Placement Spillway Closure Project

## Slide 39
Grouting South Spillway Pipes Spillway Closure Project

## Slide 40
Northeast Dike Prior to Slope Improvement Project

## Slide 41
Typical Cross-Section from Northeast Dike Slope Improvement Project

## Slide 42
Northeast Dike Slope Improvements Following Completion

## Slide 43
Northeast Dike Slope Improvements Following Completion

## Slide 44
Northeast Dike Slope Improvements Following Completion

## Slide 45
Northeast Dike Slope Improvements During Record KY Lake Pool Level

## Slide 46
Graded Filter Construction at Seep 3A Southeast Dike Slope Improvements

## Slide 47
Southeast Dike Slope Improvements During Construction

## Slide 48
Southeast Dike Slope Improvements During Record KY Lake Pool Level

## Slide 49
Southeast Dike Slope Improvements During Record KY Lake Pool Level

## Slide 50
Routine Handling, Operations & Maintenance Improvements
    Removed 860,000 tons Ash during 2010 or approximately 1/6 of the total ash impounded at the site.

## Slide 51
“Post-Remediation” Slope Stability Factors of Safety

## Slide 52
  In early 2009, TVA began an aggressive risk reduction program that included:
    Phase 1 Assessments
    Phase 2 Studies (Geotechnical/Hydraulics & Hydrology)
    Improvements to Routine Handling , Maintenance & Operations
    Capital Improvement Projects
    Hazard Classifications, Dam Safety Training, etc.;
  The JOF Risk Reduction Program for Ash Disposal Area No. 2 is the first to be completed :
    Addressed all freeboard and spillway concerns;
    Addressed all slope instability and areas with seepage issues;
    Removed excess stockpiled ash and dried out the northern half of the island;
    Improved mowing and vegetation removal, elimination of animal burrows
Johnsonville Ash Disposal Area 2 Summary & Conclusions

## Slide 53
  Highlights achieved at JOF:
    Attained Tennessee State Dam Safety Program for an existing Significant Hazard structure;
    Completed design and capital improvements on timely and cost efficient manner.
    All works were done safely while facility maintained its fully operational status;
    No environmental permit violations or issues;
    No reportable safety incidents.
    Well-documented “Lessons Learned” for future Risk Reduction projects at other TVA facilities.
    All this while having lots of fun along the way.
Johnsonville Ash Disposal Area 2 Summary & Conclusions

## Slide 54: Clowns in the Trench
We hope you enjoyed our presentation ! Any Questions?
I hope that they don’t ask any questions about PPD!